## Agile Plan
Sprint | Milestone | Objective | Tasks | Start Date | End Date | Status
Sprint 1 | Data Collection & Preprocessing | Build cleaned dataset | Collect dataset; Handle missing values; Encode categorical features; Create target label | 01-Jan | 10-Jan | Completed
Sprint 2 | EDA & Feature Engineering | Derive insights and prepare features | Perform EDA; Visualizations; Correlation analysis; Feature engineering | 11-Jan | 18-Jan | Completed
Sprint 3 | Predictive Modeling | Train regression models | Train Linear Regression; Random Forest; Gradient Boosting; Evaluate MAE/RMSE/R2; Model tuning | 19-Jan | 28-Jan | Completed
Sprint 4 | Web App Development & Deployment | Build prediction web tool | Create frontend form; Connect ML backend; Deploy app; Testing | 29-Jan | 10-Feb | Completed